## Sheet1
Stage | Step | Owner | Task | Task details | Comments
Discovery | 1 | BA | Key Stroke | Contains all the steps of the process if done manually with every detail and Screenshots. Especially Output
Documentation | 2 | BA | PDD | A Process Design Document will be prepared with all the details of the process Ex: Business Exceptions etc | Sign off from BA
| 3 | SA | SDD | A Technical document explaining artichtecture of the process mainly along with other details like Ex: Assets to be used
Development | 4 | DEV | Development Team | Development > Unit test cases | Code pushed to Dev Orchestrator
| 5 | DEV | Code Review | By SA/PM/PEER | Code pushed to Dev Orchestrator if required
Deployment | 5.5 | Orchestrator Admin Team | Deployment | Dev data is deployed on NFT/ Testing Orch
Testing | 6 | Testing team/Dev | Testing | Test the bots as per PDD and testing standards | Defects found
Dev | 7 | DEV | Defect Fixing | Bug are fixed in DEV Env and Push the code to NFT Orchestrator | DFID- 1 Prioroty P1
DFID- 2 Prioroty P1
DFID- 3 Prioroty P2
DFID- 4 Prioroty P3
Deployment | 7.5 | Orchestrator Admin Team | Deployment | Dev data(code with fixes) is deployed on NFT/ Testing Orch
Testing | 8 | Testing Team/Dev | Testing | Defect fix validation | If All Good - Sign OFF
UAT Testing | 9 | BA | UAT Testing | Business team tests bots as per PDD | If All Good - Sign OFF
Deployment | 10 | Orchestrator Admin Team | Deployment | Push the code to Prod Orchestrator
Maintenance | 11 | BA/SA/DEV | Hypercare | HC Phase - 2 weeks if bot runs daily HC Phase - 2 weeks if bot runs 24/7 with more test data | No Bugs - All good
| 12 | Support Team | L1 - Support team | L1 - for Minor changes. Not related to Code - Ex: Asset, Trigger, Logs
|  |  | L2 - Support + Dev | L2 - Minor change in Code - Both support and Dev Ex: Email changes from SMTP to Exchange
|  |  | L3 - COE | L3 - Support team will reach out to COE for any code changes, changes in architecture, or bot failures due to the isssue which are outside of code Ex: Application issues occurred on latest Windows upgrade/patch | Ex: COE team will reachout to Microsoft and find the root cause the issue and provide the solution/information to the Dev team